## Product Backlog
Planned Sprint | Actual Sprint | US ID | User Story Description | MOSCOW | Dependency | Assignee | Status
Sprint 1 | Sprint 1 | US-1 | Setup project environment (JDK, IntelliJ) | MUST HAVE |  | Ponabinanth.S | 3- Completed
Sprint 1 | Sprint 1 | US-2 | GitHub Desktop and MySQL Setup | MUST HAVE |  | Ponabinanth.S | 3- Completed
Sprint 1 | Sprint 1 | US-3 | Implement Product model & InventoryManager with OOP | MUST HAVE |  | Ponabinanth.S | 3- Completed
Sprint 1 | Sprint 1 | US-4 | Exception Handling Implement persistence with CSV & Git workflow | MUST HAVE |  | Ponabinanth.S | 3- Completed
Sprint 2 | Sprint 2 | US-5 | Database basics: SQL practice + JDBC connection test | MUST HAVE |  | Ponabinanth.S | 3- Completed
Sprint 2 | Sprint 2 | US-6 | Implement Read Operations (getAll, getById) & Console Menu Integration | MUST HAVE |  | Ponabinanth.S | 3- Completed
Sprint 2 | Sprint 2 | US-7 | Integrate CRUD into Console Menu (End-to-End Test) | MUST HAVE |  | Ponabinanth.S | 3- Completed
Sprint 2 | Sprint 2 | US-8 | Add Input Validation & Error Handling | MUST HAVE |  | Ponabinanth.S | 3- Completed
Sprint 2 | Sprint 2 | US-9 | Junit testing | MUST HAVE |  | Ponabinanth.S | 3- Completed
Sprint 3 | Sprint 3 | US-10 | Implement CSVHelper for exporting inventory data | MUST HAVE |  | Ponabinanth.S | 3- Completed
Sprint 3 | Sprint 3 | US-11 | Create and Implement the user class | MUST HAVE |  | Ponabinanth.S | 3- Completed
Sprint 3 | Sprint 3 | US-12 | Implement EmailService to send reports via SMTP | SHOULD HAVE |  | Ponabinanth.S | 3- Completed
Sprint 3 | Sprint 3 | US-13 | Implement and verify the Mockvita test cases | MUST HAVE |  | Ponabinanth.S | 3- Completed
Sprint 3 | Sprint 3 | US-14 | Integrate DB + CSV + Email modules for full reporting | SHOULD HAVE |  | Ponabinanth.S | 3- Completed
Sprint 3 | Sprint 3 | US-15 | Add “Generate Report” option in Admin Menu | COULD HAVE |  | Ponabinanth.S | 3- Completed
Sprint 4 | Sprint 4 | US-16 | Implement OTP-based user verification during registration | MUST HAVE |  | Ponabinanth.S | 3- Completed
Sprint 4 | Sprint 4 | US-17 | Add “Verify Email” & “Resend OTP” | MUST HAVE |  | Ponabinanth.S | 3- Completed
Sprint 4 | Sprint 4 | US-18 | Implement the Stock Alert Service class | MUST HAVE |  | Ponabinanth.S | 3- Completed
Sprint 4 | Sprint 4 | US-19 | options in main menuImplement stock monitoring logic for low-stock alerting | MUST HAVE |  | Ponabinanth.S | 3- Completed
Sprint 5 | Sprint 5 | US-20 | Develop and schedule automated stock alert generator | MUST HAVE |  | Ponabinanth.S | 3- Completed
Sprint 5 | Sprint 5 | US-21 | Integrate email notifications for low-stock products | MUST HAVE |  | Ponabinanth.S | 3- Completed
Sprint 5 | Sprint 5 | US-22 | Implement and verify the Mockvita test cases | MUST HAVE |  | Ponabinanth.S | 3- Completed
Sprint 5 | Sprint 5 | US-23 | Package and deploy full inventory management system | MUST HAVE |  | Ponabinanth.S | 3- Completed
Sprint 6 | Sprint 6 | US-24 | Implement MIT Lisence to the project structure | MUST HAVE |  | Ponabinanth.S | 3- Completed
Sprint 6 | Sprint 6 | US-25 | Create the presentation for the project | MUST HAVE |  | Ponabinanth.S | 3- Completed